## README
Alma Insights — Enablement Pilot UAT Tracker
Pilot window: Jul 20 – Aug 14, 2026 · 1 pilot specialist · Companion to the Program Overview doc
How to use | One tab per pilot week (prefilled test cases — edit freely, they are suggestions, not scripture). Fill the yellow cells only: Status, Severity, Build tested, Date, Notes. Log every defect in Bug Log and every release in Update Log. Score the Scorecard tab at the end of each week.
Legend | Yellow cells = you fill these in. Everything else is fixed text. Dropdowns are provided for Status, Severity, and scores.
Status key | Not run · Pass · Fail (log a bug) · Blocked (dependency missing, e.g. Slack approval) · N/A
Severity key | P0 blocks daily work · P1 major function broken, workaround exists · P2 minor · P3 cosmetic
Score rubric (1–5) | 1 = doesn't work / wouldn't use · 2 = works occasionally, high friction · 3 = usable with workarounds · 4 = good, minor gaps · 5 = excellent — better than my current workflow
Weeks | Week 1 Jul 20–24 Setup · Week 2 Jul 27–31 Core workflows + Zendesk emulation + first auto-update · Week 3 Aug 3–7 Slack (if approved) + full suite · Week 4 Aug 10–14 Polish & regression
Assumptions | Weeks run Monday–Friday starting Jul 20, 2026. Zendesk is emulated via a Drive mirror folder (never connected live). CI/CD cases start Week 2. Example rows in Bug Log and Update Log are marked EXAMPLE — replace them with real entries.

## Scorecard
# | Dimension | What we're asking | Week 1 | Week 2 | Week 3 | Week 4 | Notes / examples that drove the score
1 | Google Drive search | When you ask for a document or an answer, does the app find the right thing, fast?
2 | Card content creation | Are card drafts and update suggestions accurate, on-voice, and usable with only light edits?
3 | Posting updates | Do publish/write flows (Guru updates, Asana changes) work reliably, safely, predictably?
4 | Comfort with the tool | How comfortable are you using it for real work without help?
Scores are 1–5 (rubric on README). Week 1 may be N/A for dimensions not yet exercised — leave blank.

## Week 1 - Setup
ID | Area | Test case | Expected result | Status | Severity (if failed) | Build tested | Date | Notes / evidence
W1-01 | Install | Install Alma Insights via the installer on the specialist's machine; first launch | App launches cleanly and reaches the Home page
W1-02 | Access — Google | Complete Google sign-in; open the Drive folder picker | Sign-in succeeds; required folders visible, including shared-with-me folders
W1-03 | Access — Drive KB | Select the knowledge folders and let indexing complete; search for a known document | The known document appears in top results
W1-04 | Access — Guru | Open the Workbench | Guru cards load and are readable
W1-05 | Access — Asana | Open the Calendar | Current Asana tasks render on the calendar
W1-06 | Access — Claude/AWS | Send Renn a first message referencing our content | Renn responds using our material; no auth errors
W1-07 | Help Center | Open the in-app Help Center | Articles load and are searchable
W1-08 | CI/CD baseline | Record the installed app version in the Update Log tab | Baseline version captured for auto-update comparison
W1-09 | Survey | Complete the pre-launch survey (tab in this workbook or Google Form) | All questions answered before first real use
W1-10 | Onboarding | Guided walkthrough session (30–45 min) | Specialist can navigate all main pages unaided afterward
W1-11 | Process | Agree the bug-reporting channel and expected response time | Specialist knows where to log issues and who to ping
W1-12 | Stability | Next-day cold start | App reopens cleanly; sign-ins and settings persisted

## Week 2 - Core + Zendesk
ID | Area | Test case | Expected result | Status | Severity (if failed) | Build tested | Date | Notes / evidence
W2-01 | Renn | Ask Renn a real content question in plain English | Grounded answer drawing on our docs, with the source identifiable
W2-02 | Drive search | Search for 5 known documents by name/topic | Each appears in the top 3 results
W2-03 | Drive search | Ask Renn to find a document described only by topic | Correct document surfaced without the exact title
W2-04 | Drive search | Import a Drive doc into the app for card work | Content imports intact and is usable downstream
W2-05 | Guru flow | From a recently changed source doc, generate a card-update suggestion | Suggestion targets the right card; proposed edit is accurate
W2-06 | Card creation | Create a new card draft from a source document | Draft is on-voice and needs only light edits
W2-07 | Posting updates | Publish a card update | Native confirmation appears; after confirming, the card updates in Guru
W2-08 | Posting updates | Start a publish, then decline the confirmation | Nothing posts; state stays clean
W2-09 | Asana flow | Create a content task (via Renn or UI) | Confirm gate shown; task appears in Asana correctly
W2-10 | Asana flow | Reschedule an existing task | Change confirmed and visible in Asana
W2-11 | Zendesk emulation | Stand up the Zendesk mirror Drive folder (macros + Support Center exports) | Folder populated and selected as a knowledge source in the app
W2-12 | Zendesk emulation | Search for a specific macro by topic | Macro found via in-app search of the mirror
W2-13 | Zendesk emulation | Draft a macro revision in the app, then copy-paste into Zendesk | Paste is clean; formatting survives; workflow feels workable
W2-14 | Zendesk emulation | Confirm no live Zendesk connection exists | No Zendesk credentials requested; app never calls Zendesk
W2-15 | CI/CD | First pushed release arrives via auto-update | Update applies with zero manual steps; version increments
W2-16 | CI/CD | Post-update health check | Settings and data intact; app relaunches clean
W2-17 | Scorecard | Score all four dimensions for Week 2 | Scorecard tab filled with notes

## Week 3 - Slack + Full Suite
ID | Area | Test case | Expected result | Status | Severity (if failed) | Build tested | Date | Notes / evidence
W3-01 | Slack (if approved) | Access the Slack interface | Slack surface reachable and signed in (mark Blocked if approval pending)
W3-02 | Slack (if approved) | Exercise the designed Slack flow (messages/notifications) | Messages flow as designed between Slack and the app
W3-03 | Slack (if approved) | Raise a content request from Slack | Request lands in the app workflow correctly
W3-04 | Full suite | End-to-end: update request → research in Drive → draft in studio → publish to Guru (gated) → close task in Asana | Entire chain completes in one sitting without leaving the app (except gated confirms)
W3-05 | Full suite | Repeat end-to-end on a second real request, unassisted | Completes without help; time taken noted
W3-06 | Stability | Full workday soak under real workload | No crashes/hangs; anything odd noted
W3-07 | CI/CD | At least one further auto-update delivered | Hands-free delivery; latency recorded in Update Log
W3-08 | Regression | Re-test every Week-2 failure on its fixing build | Fixed cases now pass; still-broken ones stay open in Bug Log
W3-09 | Scorecard | Score all four dimensions for Week 3 | Scorecard tab filled with notes

## Week 4 - Polish + Regression
ID | Area | Test case | Expected result | Status | Severity (if failed) | Build tested | Date | Notes / evidence
W4-01 | Bugs | Every open bug fixed or explicitly deferred | Bug Log shows no undispositioned entries
W4-02 | Regression | Re-run every case that ever failed, on the final build | ≥ 90% of all UAT cases pass
W4-03 | Full experience | Specialist runs their real workload all week without assistance | No blocking issues; friction points noted
W4-04 | CI/CD | Update Log review | ≥ 3 hands-free updates over the pilot; zero manual reinstalls
W4-05 | Scorecard | Final scores for all four dimensions | Week 4 column complete; averages ≥ 4 is the go bar
W4-06 | Survey | Complete the post-launch survey | All questions answered
W4-07 | Wrap-up | Wrap-up interview held | Keep / change / drop captured; quotes recorded
W4-08 | Readout | Go/no-go readout assembled from this workbook | Decision made with scores, bug record, and update record attached

## Bug Log
Bug ID | Date found | Area | Description (what happened vs. expected) | Severity | Status | Fixed in build | Verified date | Notes
BUG-001 | 2026-07-28 | Drive search | EXAMPLE — Search for 'refund macro' returned no results although the doc exists in the mirror folder; expected top-3 hit. | P1 - major | Fixed | 1.4.2 | 2026-07-30 | Re-tested on 1.4.2, passes. Replace this row with real entries.

## Update Log
Release / version | Pushed (date & time) | Received on pilot machine (date & time) | Hands-free? (no manual steps) | App healthy after update? | What changed (release note) | Notes
1.4.2 | 2026-07-29 14:00 | 2026-07-29 16:10 | Yes | Yes | EXAMPLE — Fix Drive search miss on mirror folder; Workbench polish. | ~2h latency. Replace this row with real entries.

## Pre-Launch Survey
Complete in Week 1 before first real use. Ready to move into a Google Form if preferred.
# | Question | Answer format | Response
1 | In a typical day, how much time do you spend finding content — docs, macros, cards? | under 15 min / 15–30 / 30–60 / over an hour
2 | How confident are you that you can find the right document in Google Drive today? | 1–5
3 | Walk us through how a card update happens today, start to finish. | free text
4 | How often do content updates sit in a backlog for more than a week? | never / sometimes / often / always
5 | How comfortable are you using AI assistants for work today? | 1–5
6 | Which tools do you rely on daily? | Drive / Guru / Asana / Zendesk / Slack / other
7 | What would make this pilot a clear win for you? | free text
8 | What is your biggest concern going in? | free text
9 | How comfortable are you troubleshooting app issues yourself? | 1–5
10 | Anything about your workflow we should know before we start? | free text

## Post-Launch Survey
Complete in Week 4, paired with the wrap-up interview.
# | Question | Answer format | Response
1 | Final rating — Google Drive search | 1–5
2 | Final rating — card content creation | 1–5
3 | Final rating — posting updates (Guru / Asana) | 1–5
4 | Final rating — comfort with the tool | 1–5
5 | How likely are you to recommend rolling this out to the rest of the team? | 0–10
6 | How was the auto-update experience — did updates ever interrupt or confuse you? | 1–5 + free text
7 | Biggest win of the month? | free text
8 | Biggest gap or frustration? | free text
9 | Name one thing to keep, one to change, one to drop. | free text
10 | Did anything ever feel unsafe, unclear, or too risky — publishing, data handling, AI behavior? | free text
11 | Compared to your pre-pilot workflow, how much time did it save per day? | none / <15 min / 15–30 / 30–60 / >1 hour
12 | Would you keep using it after the pilot? | yes/no + why